## Sheet1
Appendix-4
Details of the Schemes whose Expenditure is funded under Special Allowance
Name of the Station: RAMAGUNDAM STPS -I&II (2100 MW)
Sl. No. | Name of Schem (including completed schemes) | Awarded/ Estimated/ Completed Value (Rs. Cr.) | Exp. Upto 31.03.2018 Rs. Cr.) | Proposed Expenditure (Rs. Cr) |  |  | Remarks/ Status
|  |  |  | 2018-19 | 2019-20 | 2020-21
1 | VAM (VAPOUR ABSORPTION MACHINE) OF 350TR CAPACITY | 0.67 | 0.6722 | 0 | 0 | 0 | Completed
2 | RETROFIT OF 132 KV AND 220 KV CIRCUIT BREAKERS | 0.85 | 0.8533 | 0 | 0 | 0 | Completed
3 | REPL OF OLD AEG 400KV CBs | 4.08 | 4.076 | 0 | 0 | 0 | Completed
4 | 400KV,220KV,132 KV CB REPLACEMENT | 0.68 | 0.6785 | 0 | 0 | 0 | Completed
5 | TRANSFORMER, 25 MVA FOR CW STAGE # I | 0.96 | 0.9611 | 0 | 0 | 0 | Completed
6 | DC CHARGERS FOR STAGE-1 UNITS AND OFF SITE AREAS | 0.82 | 0.8171 | 0 | 0 | 0 | Completed
7 | REPL OF MOCB UNIT SWGR OF UNIT-1&2 OF STAGE-1 WITH NEW SWGR WITH VACCUM BREAKERS | 4.55 | 4.5533 | 0 | 0 | 0 | Completed
8 | REPLACEMENT OF GENERATOR - 1, 2 & 3 PROTECTION PANELS | 2.04 | 2.0355 | 0 | 0 | 0 | Completed
9 | RENOVATION OF STAGE-1 LIFTS | 1.85 | 1.85 | 0 | 0 | 0 | Completed
10 | PROCUREMENT OF STAGE-1 CW PUMP MOTORS | 3.13 | 3.1295 | 0 | 0 | 0 | Completed
11 | RENOVATION OF 400KV ISOLATOR ARMS | 0.73 | 0.7315 | 0 | 0 | 0 | Completed
12 | SUPPLY, ERECTION & COMMNG OF EARTH SWITCH M.O.M BOXES FOR 400 kV, 2000 A, HCB ISOLATORS | 0.5 | 0.4979 | 0 | 0 | 0 | Completed
13 | REPL OF 420 KV CVTs AND 132 KV CVTs | 0.71 | 0.7078 | 0 | 0 | 0 | Completed
14 | PROCUREMENT OF 220kV CVTs | 0.12 | 0.1161 | 0 | 0 | 0 | Completed
15 | 400KV CTs (TELK Make) | 3.86 | 3.8568 | 0 | 0 | 0 | Completed
16 | Repl of CT/CVT & LT Transf -400KV Swyd | 0.05 | 0.0514 | 0 | 0 | 0 | Completed
17 | RETROFIT OF NGEF AIR CBs WITH NEW BREAKERS & PROT. RELAYS IN STAGE-1 LT SWGR | 1.52 | 1.5213 | 0 | 0 | 0 | Completed
18 | 315 KVA LT TRANSFORMER | 0.12 | 0.1171 | 0 | 0 | 0 | Completed
19 | 1600 KVA LT TRANSFORMER | 0.44 | 0.4366 | 0 | 0 | 0 | Completed
20 | NEW SWITCH YARD SERVICE TRANSFORMER, 630 KVA, 33 KV / 433 VOLTS | 0.06 | 0.0618 | 0 | 0 | 0 | Completed
21 | CCTV SYSTEM FOR STAGE-I MAIN PLANT & OFFSITES | 2.95 | 2.9526 | 0 | 0 | 0 | Completed
22 | UPGRADATION OF VGF IN CHP | 3.41 | 3.4084 | 0 | 0 | 0 | Completed
23 | R&M works of VGFs in CH-II | 0.26 | 0.263 | 0 | 0 | 0 | Completed
24 | FABRICATED GEAR BOX SZN 360 FOR CONVEYORS 19 A/B | 0.26 | 0.2645 | 0 | 0 | 0 | Completed
25 | BIFURCATION OF COMMON CHUTE OF CONVEYOR 2A/B IN CHP | 3.38 | 3.3771 | 0 | 0 | 0 | Completed
26 | REPLACEMENT OF HOISTS IN CHP | 2.62 | 2.6178 | 0 | 0 | 0 | Completed
27 | REPL OF HOISTS IN CHP (17 nos.) | 1.34 | 1.3444 | 0 | 0 | 0 | Completed
28 | BD-355 BULLDOZER BEML MAKE WITH BS6WD170 ENGINE WITH OPERATOR CABIN | 2.01 | 2.006 | 0 | 0 | 0 | Completed
29 | BD-14W WHEEL DOZER BEML MAKE WITH BSA6D105 ENGINE WITH OPERATOR CABIN | 1.22 | 1.2163 | 0 | 0 | 0 | Completed
30 | SUPPLY& ASSISTANCE IN ERECTION & COMMNG OF 3 NOS OF CHLORINATOR STREAMS WITH A CAPACITY OF 150 kg/hr. | 0.45 | 0.4511 | 0 | 0 | 0 | Completed
31 | ASSISTANCE IN ERECTION , COMMNG & PERFORMANCE TESTING OF 3 SETS OF 150kg/hr CHLORINATORS | 0.01 | 0.0138 | 0 | 0 | 0 | Completed
32 | 3 SETS OF CHLORINATORS OF 40 kg/hr CAPACITY FOR STAGE- I PTP CHLORINATION SYSTEM | 0.41 | 0.4123 | 0 | 0 | 0 | Completed
33 | RENOVATION OF AIR COMPRESSORS IN STAGE-I | 5.04 | 5.0441 | 0 | 0 | 0 | Completed
34 | INSTALLATION OF CPU IN STAGE -I UNITS | 14.62 | 2.0638 |  |  | 12.5562 | Detailed engg & layout finalisation in process
35 | RENOVATION OF GT -1 NO | 9.54 | 9.544 | 0 | 0 | 0 | Completed
36 | PROCUREMENT OF 34 NOS. BOBR WAGONS | 10.72 | 10.7222 | 0 | 0 | 0 | Completed
37 | PROCUREMENT OF 288 NOS. WAGON WHEEL & AXLES ASSY (W/o BEARINGS) | 7.32 | 7.3171 | 0 | 0 | 0 | Completed
38 | BEARINGS FOR WHEEL & AXLES ASSY | 0.71 | 0.7051 | 0 | 0 | 0 | Completed
39 | DDCMIS- MAIN PLANT C&I U # 1-3 (3x200MW) | 45.44 | 44.4416 | 1 | 0 | 0 | Completed
40 | R&M OF MAIN PLANT TG U # 1-3 (3x200MW) | 375.15 | 60.0168 | 192 | 77 | 46.13 | Awarded / under implementation
41 | ESP St-1 (3X200 MW) | 122.29 | 11.6425 |  |  | 110.6475 | Awarded
42 | Uprating of Auxiliaries and related Boiler works ( TPT, Blr Perf Streamlining, APH, Mills, PAF, IDF, LP Econ) | 91.44 | 0 |  |  | 91.44 | To be awarded
43 | Up-gradation of UCR AC System with Screw Chiller system | 4.95 |  |  |  | 4.95 | To be awarded
44 | Additional Economizer coil bank in two units along with replacement of existing coil. | 7.94 | 0.087 | 7.8552 | 0 |  | Awarded
45 | Replacement of Metallic Expansion joints in Air & Flue Gas path | 7.74 |  | 2.5 | 5.24 |  | Awarded
46 | Hoists in Boiler area (Mills for 03 Units & workshop - 37 nos.) | 1.91 |  |  |  | 1.91 | To be awarded
47 | Upgradation of DM Plant PLC & Control System | 2.43 |  |  |  | 2.43 | To be awarded
48 | CCTV System | 6.37 |  |  |  | 6.37 | To be awarded
49 | Renovation of Elevators(Main Plant & CHP) with VFD control | 10.31 |  |  |  | 10.31 | To be awarded
50 | Replacement of all DPRs & Equalizing valves for Generator SOS | 3.5 |  |  |  | 3.5
51 | Renovation of Conveyor 13A/B with new mechanicals (inclusive of total conveyor alignment) | 1.44 | 0.3303 | 1.1097 | 0 |  | Awarded
52 | EXTENSION OF CONV 22A/B & CONNECTION TO 9A/B | 16.25 |  |  |  | 16.25 | To be awarded
53 | Replacing the existing Chlorinators for CW System(Stage-II) | 1.45 |  |  |  | 1.45
54 | Chlorine Dioxide Dozing system for CW System (Stage-II) | 0.62 |  |  |  | 0.62
55 | Hoists 05 nos (LWTP-2 nos, AWPH-2 nos, CWPH-1 no.) | 0.36 |  |  |  | 0.36 | To be awarded
56 | Installation of fourth pump in Fly Ash disposal series of Stage-II | 3.07 |  |  |  | 3.07 | To be awarded
57 | Hoists 03 nos (DAETP compr room -5T), ASPH: St-1(6T),St-2 (7.5T) | 0.29 |  |  |  | 0.29 | To be awarded
58 | Renovation and extension of storage shed | 1.3 |  |  |  | 1.3 | To be awarded
59 | HP Heaters 5A & 5B replacement | 8.63 |  |  |  | 8.63 | To be awarded
60 | Up gradation of CPU | 27.59 |  |  |  | 27.59 | To be awarded
61 | Wall RH removal and increase RH | 74.75 |  |  |  | 74.75
62 | Procurement of Additional Diesel Locomotive (Two no.) | 24 |  |  |  | 24 | To be awarded
63 | 34 wagons | 14.08 |  |  |  | 14.08 | To be awarded
64 | Renovation of Turbine Governing system devices & Retrofit of EHC Plunger Coil for Turbine and TDBFP-A,B | 36.36 |  |  |  | 36.36 | To be awarded
65 | RLA Study & Replacement of Critical Piping Hangers & Supports (St-1 &2) | 20.31 | 1.599 |  |  | 18.71 | Awarded
66 | ESP Stage-2(3X500 MW) | 235.71 |  |  |  | 235.71 | To be awarded
67 | CENTRALISED A/C OF SERVICE BUILDING | 4.4 | 0 |  |  | 4.4 | To be awarded
| Total | 1244.09 | 199.5656 | 204.4649 | 82.24 | 757.8137