## Sheet1
Appendix-2
Details of the Schemes whose Expenditure is funded under Special Allowance
Name of the Station: KORBA Stage-I&II (2100 MW)
Sl. No. | Name of Scheme (including completed schemes) | Awarded/ Estimated/ Completed Value (Rs. Cr.) | Exp. Upto 31.03.2018 (Rs. Cr.) | Proposed Expenditure (Rs. Cr) |  |  | Remarks/ Status
|  |  |  | 2018-19 | 2019-20 | 2020-21
1 | ESP Modification | 296.9 | 259.47 | 15.82 | 21.61 |  | under implementation
2 | DDCMIS Stage-I | 39.12 | 37.72 | 1.37 | 0 |  | under implementation
3 | DDCMIS Stage-II | 65.53 | 63.3 | 2.08 | 0.05 |  | under implementation
4 | RLA of critical piping hangers & supports in St-I | 3.71 | 0 | 1.2243 | 2.4857 |  | under implementation
5 | Supply of guillotine gates at FD fans outlet in stage-I | 1.33 | 1.33 |  |  |  | Completed
6 | Renovation of Insulation and refractory in Boilers of 3x200 MW units:A) General replacement of insulation and aluminium cladding sheet(i) | 0.08 | 0.08 |  |  |  | completed
7 | Renovation of Insulation and refractory in Boilers of 3x200 MW units: A) General replacement of insulation and aluminium cladding sheet(ii) | 0.43 | 0.43 |  |  |  | completed
8 | Renovation of Insulation and refractory in Boilers of 3x200 MW units:A) General replacement of insulation and aluminium cladding sheet (iii) | 0.59 | 0.59 |  |  |  | completed
9 | Renovation of Insulation and refractory in Boilers of 3x200 MW units:A) General replacement of insulation and aluminium cladding sheet (iv) | 0.05 | 0.05 |  |  |  | completed
10 | Renovation of Insulation and refractory in Boilers of 3x200 MW units:A) General replacement of insulation and aluminium cladding sheet (v) | 1.69 | 1.69 |  |  |  | completed
11 | Renovation of Insulation and refractory in Boilers of 3x200 MW units:A) General replacement of insulation | 0.88 | 0.44 | 0.44 |  |  | under implementation
12 | ALU cladding sheet | 0.93 | 0.93 |  |  |  | completed
13 | Replacement of St.-I Main Turbine Oil Cooler tube nest assembly | 1.22 | 1.22 |  |  |  | completed
14 | Main steam strainer housing replacement of 3x200MW units | 1.77 | 1.77 |  |  |  | completed
15 | Replacement of LP Turbine compensators in St.-I, 3x200MW | 0.31 | 0.31 |  |  |  | completed
16 | a) Renovation of existing Bipolar Electrolyser & Rectifier in hydrogen plant | 2.65 | 0 | 2.65 |  |  | under implementation
17 | R&M of stage-I Generator Protection System (Due to obsolescence) & Disturbance recorders | 2.31 | 2.31 |  |  |  | completed
18 | Renovation and modernization of Unit-1 & 3 lift | 0.81 | 0.81 |  |  |  | completed
19 | Renovation and modernization of OTIS make Elevators in the plant & Adm Building | 0.91 | 0.91 |  |  |  | completed
20 | Supply and retrofitting of 3 -pole vacuum/ SF6 Breaker in place of existing 6 pole MOCBs , Stage-I HT Sw. gr. Protection Up- gradation & renovation ,R&M of 6.6KV /11KV NGEF Switchgears | 12.1 | 11.63 | 0.47 |  |  | under implementation
21 | Generator Protection Cabling | 0.69 | 0.69 |  |  |  | completed
22 | Procurement of Feeder Pillar Boards and LDBs in Stage-I | 0.15 | 0.15 |  |  |  | completed
23 | Procurement of Lighting Fixtures For Stage 1 R&M | 0.21 | 0.21 |  |  |  | completed
24 | Procurement of Lighting Transformer under R&M | 0.14 | 0.14 |  |  |  | completed
25 | Procurement of Cables For R&M In Lighting and Welding | 0.17 | 0.17 |  |  |  | completed
26 | Procurement of Conduits and Accessories for Lighting Stage 1 R&M | 0.21 | 0.21 |  |  |  | completed
27 | Procurement of "universal automatic relay test kit with sampled values" for NTPC-Korba SWYD area. | 0.33 | 0.33 |  |  |  | completed
28 | 25.5 meter Aerial working platform for SWYD, under st-I R&M tools. | 0.82 | 0.82 |  |  |  | completed
29 | Procurement of 10KL oil filtration Plant for power transformers | 0.26 | 0.26 |  |  |  | completed
30 | Transformer oil moisture measurement kit | 0.1 | 0.1 |  |  |  | completed
31 | Electrical Testing Instrument : Insulation Tester | 0.5 | 0.5 |  |  |  | completed
32 | Replacement of 6.6 KV Power Cables in ST-I 6.6 KV System(I) | 3.24 | 3.24 |  |  |  | completed
33 | Replacement of 6.6 KV Power Cables in ST-I 6.6 KV System(II) | 0.04 | 0.04 |  |  |  | completed
34 | Replacement of 6.6 KV Power Cables in ST-I 6.6 KV System(III) | 0.76 | 0.76 |  |  |  | completed
35 | Replacement of 6.6 KV Power Cables in ST-I 6.6 KV System (IV) | 0.24 | 0.08 |  | 0.16 |  | under implementation
36 | Renovation of Stage-I steam generators feeder control system | 5.59 | 5.59 |  |  |  | completed
37 | Renovation of St.-I Raw water pumps (01 no.) | 0.49 | 0.49 |  |  |  | completed
38 | Replacement of existing Instrument and plant air compressors with screw compressors in Stage – I | 4.26 | 3.8 | 0.46 |  |  | under implementation
39 | Phasing out of Halon Fire Protection system with inert gas fire extinguishing system in St-1 (3 x 200 MW) units of Korba STPS. | 3.81 | 2.52 | 1.29 |  |  | under implementation
40 | Renovation of Hoists of Track hopper-I, conveyor-2A/B drive, crusher house-I, TP-3, TP-4, conv-6A/B drive, stack yard (Nos.-33) | 1.55 | 0.28 | 1.27 |  |  | under implementation
41 | Renovation of empty rails from T -18 (52KG, 72UTS), 2nd quality to T-12 (60KG, 90UTS)1st quality - rails only | 10.08 | 10.08 |  |  |  | completed
42 | Renovation of empty rails from T -18 (52KG, 72UTS), 2nd quality to T-12 (60KG, 90UTS)1st quality - service contract | 2.3 | 2.3 |  |  |  | completed
43 | Renovation of empty rails from T -18 (52KG, 72UTS), 2nd quality to T-12 (60KG, 90UTS)1st quality - auxiliary spares(I) | 0.06 | 0.06 |  |  |  | completed
44 | Renovation of empty rails from T -18 (52KG, 72UTS), 2nd quality to T-12 (60KG, 90UTS)1st quality - auxiliary spares(II) | 0.36 | 0.36 |  |  |  | completed
45 | Conversion of conveyor dual drives into single drive (2A/B, 4A/B & 13A/B) (i) | 0.3 | 0.3 |  |  |  | completed
46 | Conversion of conveyor dual drives into single drive (2A/B, 4A/B & 13A/B)(ii) | 0.33 | 0.33 |  |  |  | completed
47 | Reliability improvement of CEP by complete assembly replacement. (1 complete assy) | 3.99 | 0 | 3.99 |  |  | under implementation
48 | Unit #5 HPT refurbishment. | 11 | 0 | 11 |  |  | 1 PO. placed
49 | Additional CW Transformer for St-I | 1.53 | 0 | 1.53 |  |  | under implementation
50 | Supply, E&C of Fire detection system for LT & HT Swgr rooms, battery bank rooms of Main plant Stage-I & Switchyard | 0.68 | 0 | 0 | 0.68 |  | PR to be raised
51 | Strengthening/ Buttressing of Existing Dyke at Dhanras Ash Dyke of NTPC Korba | 43.87 | 7.11 | 36.76 |  |  | under implementation
52 | Height Raising after Buttressing(5th Raising of Lagoon-I) | 17.58 | 15.62 | 1.96 |  |  | under implementation
53 | Height Raising After Buttressing(6th Raising of Lagoon-I) | 9.96 | 5.03 | 4.93 |  |  | under implementation
54 | Pipe line procurement and laying | 4.93 | 4.93 |  |  |  | completed
55 | Continuous Emission Monitoring System (CEMS) | 1.71 | 1.71 |  |  |  | completed
56 | Phasing out of Halon Fire Protection System. | 3.55 | 3.55 |  |  |  | completed
57 | Supply & Installation Effluent Quality Monitoring System (EQMS) | 0.34 | 0.34 |  |  |  | completed
58 | T&P for Plant & Machinery | 20.55 | 1.04 | 0.6 | 18.91 |  | 71 nos. PR raised
59 | Renovation of Township | 11.36 | 0.27 | 2.57 | 8.52 |  | balance pr To Raise
60 | Reciprocating air compressor replacement with screw type air compressor for less maintenance and lube oil consumption | 5.43 | 0 |  | 5.43 |  | PR raised
61 | Replacement of DM make-up line from MSRL to SS line unit-4,5,6 | 2.39 | 0 | 1.3 | 1.09 |  | Material PR raised,Service PR to be raised
62 | Replacement of power cables of Mill motors, ID fan motors, all LT drives and Excitation system cables. | 7.5 | 0 | 3.75 | 3.75 |  | PR raised
63 | Replacement of Protection cables from GRP to Switchyard. | 1.19 | 0 | 1.19 |  |  | PR raised
64 | Replacement of Servo/Blocking units of HP Bypass control v/v actuators with Proportional valves and Replacement of HP Bypass system oil supply units. | 13.83 | 0 | 13.83 |  |  | PR raised
65 | Repairs and Protection work of RCC Structure of Cooling Tower Stage-II | 12.66 | 0 | 5.064 | 7.596 |  | under implementation
66 | Renovation of RCC Structure Of Stage 2 Chimneys | 7.59 | 0 | 7.59 |  |  | PR raised
67 | Replacement of 400 KV Bus-Bar Protection system | 1.86 | 0 |  | 1.86 |  | PR to be raised
68 | Civil Works For Repairs & Modernisation of different control rooms under Stage - II R&M | 1.38 | 0 |  | 1.38 |  | PR to be raised
69 | Replacement of Splash bars with fills in CT 4A,4B,6A & 6B | 13.75 | 0 | 5.5 | 8.25 |  | under implementation
70 | Augmentation of Fire Detection & Protection system for Wagon tippler of NTPC Korba | 6.7 | 0 |  | 6.7 |  | PR raised
71 | Butressing of Lagoon 2 & 3 combined and subsequent height raisings. | 64.44 | 8.22 | 30 | 26.22 |  | under implementation
72 | DPR & Detailed Engg. of Bridge over Hasdeo river including approach on either side (Khoraighat Ash dyke scheme) | 918 | 1.48 |  |  | 916.52 | under implementation balnce PR to raise
73 | Ash Dyke Saliabhata/Ghamota Land acquasition | 265.85 | 0.37 | 19.6 |  | 245.88 | PR to raise
74 | 4 no. loco WDG3A | 47.25 |  | 13.4 |  | 33.85 | PR raised
75 | WAGONS BOBRN | 25.83 |  | 23.56 |  | 2.27 | PR raised
76 | IFM Ignitors with HEA Ignitors | 9.84 |  |  | 4.26 | 5.58 | PR raised
77 | Construction of retaining wall for Coal yard. | 1.68 |  |  | 1.68 |  | PR raised
78 | Enhancement of Return Water from Dhanras Ash Dyke Lagoon-3. | 8.84 |  |  | 8.84 |  | PR to be raised
| Total | 2017.37 | 468.47 | 215.1983 | 129.4717 | 1204.1