## Sheet1
Appendix-5
Details of the Schemes whose Expenditure is funded under Special Allowance
Name of the Station: Vindhyachal STPS Stage-I (1260 MW)
Sl. No. | Name of Scheme (including completed schemes) | Awarded/ Approved/ Estimated Value (Rs. Cr.) | Exp. Upto 31.03.2018 Rs. Cr.) | Proposed Expenditure (Rs. Cr) |  |  | Remarks/ Status
|  |  |  | 2018-19 | 2019-20 | 2020-21
1 | TG aux. area pumps including Lube oil pump, hydrogen seal oil pump, drip pump etc. - Replacement (66 no) | 5.41 | 0 | 0 | 5.41 |  | Award value considered as PR estimate value . Under QR approval
2 | Condenser tubes Replacement in all 03 units (supply) | 20.28 | 0 | 10 | 5.28 | 5 | Award value considered as PR estimate value .Under QR approval
3 | LP HTR -4 with Shell | 6.36 | 0 | 0 | 6.36 |  | Award value considered as PR estimate value . PR Under release
4 | SCAPH system Up-gradation (in 06 Units) | 1.67 | 0 | 1 | 0.67 | 0 | Award value considered as PR estimate value.Under QR approval
5 | SADC, PADS, HADS, CADS, MADS ID/FD inlet/outlet dampers with actuator Replacement (450 no) | 6.2 | 0 | 0 | 4 | 2.2 | Award value considered as PR estimate value . PR Under release
6 | Online lubricating oil cleaning system on XRP-803 Mills Installation (36 no) | 9.46 | 0 | 0 | 7 | 2.46 | Award value considered as PR estimate value. Under QR approval
7 | Boiler side valves Replacement (552 no different valves) | 12.68 | 0 | 12.68 |  |  | Awarded
8 | Damaged /faulty boiler stair cases, platform grills, hand rail - Rectification /replacement. | 45.4 | 0 | 0 | 0 | 45.4 | NIT to be issued
9 | Insulation and cladding sheet of boiler - Replacement | 5.58 | 0 | 0 | 3.58 | 2 | NIT to be issued
10 | Platen SH Attemperation headers and CRH attemperation headers along with spray system - Replacement (SH attemperation: 24 no, RH attemperation: 12 no) | 7.77 | 0 | 7.77 | 0 | 0 | Under Award approval
11 | Boiler structure strengthening /replacement and provision of access to wall below 12mtr elevation and above penthouse roof. | 3.16 | 0 | 0 | 0 | 3.16 | NIT to be issued
12 | Low point drains and economizer drain system Modification | 2.54 | 0.25 | 2.29 | 0 | 0 | Awarded
13 | All PA fan outlet Gate with actuators – Installation (36 nos) | 2.32 | 0 | 0 | 1.32 | 1 | PR to be raised
14 | PT plant St-I CCF-1,2,3 & 4 and Acid tiles, alum storage area etc. - Repair | 3.96 | 0 | 0 | 1.96 | 2 | PR under release
15 | Fire protection system- Renovation (1 lot) | 1.38 | 0 | 0.35 | 1.03 | 0 | Tender document under preperation .
16 | Plant & Instrument air Compressor- Renovation (08 no) | 2.14 | 0 | 0 | 1.14 | 1 | Under QR approval
|  | 4.05 | 0 | 2 | 2.05 | 0 | Under award approval
17 | DG sets Replacement (06 sets) | 1.89 | 0 | 1 | 0.89 | 0 | BID extended under QR query.
19 | Poly Aluminum Chloride (PAC) dozing system of PT plant - Installation (02 sets) | 0.47 | 0 | 0 | 0.47 | 0 | Note for QR finalization to be moved
20 | DM make up pumps and DM Emergency Make up pumps in All Station Pump House St-I App. Val:48 | 0.42 | 0 | 0 | 0.42 | 0 | PR under release
21 | USSR make Generator Relay Panels – Replacement (06 set) | 3.33 | 0 | 0 | 2 | 1.33 | Under NIT
22 | Existing Boiler lifts Replacement (05 no). | 3.9 | 0 | 0 | 2 | 1.9 | To be awarded
23 | Main Plant HT Switch Gear Up-gradation | 19.87 | 0 | 0 | 13 | 6.87 | Under QR finalization
24 | 220V DCDB (06 no) , 0.4 KV LT Switchgear of main plant and off site (52 No) - Replacement | 3.5 | 0 | 0 | 2 | 1.5 | Under QR preperation
25 | Upgradtion of of 400 KV SWYD , protection and control system with bay-kiosk and SAS system with 17 nos. cktbkrs, CTs, CVTs / 132 KV CT, 13KV LA, control and relay panels, Busbar panels along with cables with SAS and Bay kiosk system of Stage – I, II 132 KV Switchyard – Replacement. | 61.79 | 0 | 25 | 15 | 21.79 | To be awarded
26 | USSR make IGV actuators of ID/FD/PA Fans - Replacement (ID: 18 No, PA:36No, FD:12 No) | 7.1 | 0 | 0 | 3 | 4.1 | PR to be raised
27 | Cable Trestle and cable Trays to Provide Over ground route to existing as well as new cables- Fabrication and Erection / Cable Trestle and cable Trays to Provide Over ground route to existing as well as new cables - Fabrication and Erection | 15.18 | 0 | 0 | 3 | 12.18 | PR to be raised
28 | DM Plant Instrumentation Upgradation : Analyzers, Guages & Transmitter | 0.45 | 0 | 0.45 | 0 | 0 | Under Award
29 | Control panel of RC Feeder upgradation with microprocessor based system (36 Nos) | 8.94 | 0 | 5.5 | 2 | 1.44 | Under Award
30 | CCTV System of STAGE – I & CHP and Installation of New Cameras in Cable Galleries of stage I, II & III – Renovation (CCTV: 213 No & Common items) | 8.13 | 0 | 5 | 1 | 2.13 | Under Award
31 | UPS system - Upgradation (UPS: 06 sets, SCVS:06 No, ACDB: 12 No) | 1.91 | 0 | 1.1 | 0.81 | 0 | Under Award
32 | SWAS Upgradation | 4.28 | 0 | 2.8 | 1 | 0.48 | Under Implementation
33 | DCS Servers. Stage 1 Up-gradation. | 3.56 | 3.2 | 0.04 | 0.32 | 0 | PO placed
34 | 200 No. Wheel Sets Procurement. | 2.19 | 0 | 0 | 2.19 | 0 | Under NIT/ Award
35 | DOM Cylinder complete procurement for CIMMCO wagons (66 Nos) | 0.25 | 0 | 0.25 | 0 | 0 | Tech. clarification from indentor pending.
36 | DOM Cylinder procurement for BSCL wagons (43 No) | 0.09 | 0 | 0.09 | 0 | 0 | price bid opened , under CS preperation.
37 | ILMS, Suspended magnets and Metal detectors of CHP - Renovation (ILMS: 04 No, SM: 02 No, MD: 06 No) | 1.35 | 0 | 1.35 | 0 | 0 | Under NIT/ Award
38 | MOCB renovation with vacuum Breaker of 6.6KV/1250A 16 nos | 0.73 | 0 | 0.73 | 0 | 0 | Under NIT/ Award
39 | Separate DC system for Coal handling plant | 0.65 | 0 | 0.65 | 0 | 0 | Under NIT/ Award
40 | Protection system renovation by Numerical relays for 6.6KV HT switchgear of CHP Stage-I (38 No) | 0.31 | 0 | 0.31 | 0 | 0 | Under Award
41 | LT MCC of CHP Stage-I for TP-4 & Track hopper #1- Replacement (TP # 4 MCC (04 No Section): 01 No. Track Hopper # 1 MCC (02 No Section): 01 No.) | 1.05 | 0 | 1.05 | 0 | 0 | Under Award
42 | Rack & Pinion Type Elevator at Crusher House of CHP St-I -Installation | 0.25 | 0 | 0.25 | 0 | 0 | Under Award
43 | Old Vibrating Feeder Motors Replacement. (04 No.) | 0.96 | 0.96 | 0 | 0 | 0 | Implemented
44 | Old PA system of CHP stage-I Replacement | 0.46 | 0 | 0.46 | 0 | 0 | Under Award
45 | Rail Track of Stacker Reclaimer of CHP Stg-I - Replacement 1 No | 2.35 | 0 | 0 | 1.35 | 1 | Under Award
46 | Travel Drive Gearboxes of Stacker Reclaimer of CHP Stg-I - Replacement (08 nos) | 0.7 | 0 | 0.7 | 0 | 0 | PO placed
47 | Construction of 02 nos retaining walls on both sides of yard conveyor no.#8 oif CHP-STg.1.App. Val: 190.85 | 1.92 | 0 | 0.95 | 0.97 | 0 | Under NIT/ Award
48 | Dredging of OFL(V-1 &V-2 Ash Dyke) | 3.77 | 0 | 3.77 | 0 | 0 | PO placed
49 | Strengthening/Buttressing of existing V-1 dyke of Stage-I | 36.8 | 0.9 | 20 | 0.9 | 15 | PO placed/ inder implementation
50 | ESP R&M BMD Budget | 218.4 | 186.95 | 18 | 7 | 6.45 | PO placed/ inder implementation
51 | Provision of Cast Basalt lined pipes & bends | 25 | 0 | 8 | 17 |  | Under QR evaluation
52 | 400 KV HCB isolator | 1.2 | 0 | 0.5 | 0.7 |  | Under Award
54 | Conversion of U# 6 Excitation system to Static Excitation System | 2.36 | 2.36 | 0 | 0 | 0 | Implemented
55 | Upgradation of ABT based energy metering system | 1.78 | 1.78 | 0 | 0 | 0 | Implemented
56 | Replacement of Ash Slurry Pump House Switchgear complete except Transformer, of Stage-I. | 1.91 | 1.89 | 0.02 | 0 | 0 | Implemented
57 | Refurbishment of 05no. Cooling Towers model 1514 of Stage-I | 5.5 | 5.5 | 0 | 0 | 0 | Implemented
58 | Additional Ash slurry pump installation to get desired head. | 2.77 | 2.77 | 0 | 0 | 0 | Implemented
59 | Replacement of Acid Storage Tanks of DM Plant Stage-I | 0.73 | 0.73 | 0 | 0 | 0 | Implemented
60 | Up-gradation of relay based control system of Stage-I Compressors, CT fans, DM plant, PT plant & All Station AC with PLC system | 3.65 | 3.65 | 0 | 0 | 0 | Implemented
Total |  | 602.21 | 210.94 | 134.06 | 116.82 | 140.39