## Sheet1
Details of the Schemes whose Expenditure is funded under Special Allowance
Appendix-8
Name of the Station: Dadri Coal Stage-I
Sl. No. | Name of Scheme (including completed schemes) | Value approved/ Awarded (Rs. Cr.) | Exp. Upto 31.03.2018 Rs. Cr.) | Proposed Expenditure (Rs. Cr) |  |  | Remarks/ Status
|  |  |  | 2018-19 | 2019-20 | 2020-21
1 | Replacement of ESP Controller and Rectiformer | 6.1546 |  | 2.17 | 3.97 |  | Prpoposed for partial shifting during 2019-24 to accommodate proposals as under
2 | Renovation of Boiler Lifts of Stage - 1 | 5.4103 |  | 5.4103
3 | Forklift 10 tonne, 04 mtr | 0.155 |  |  | 0.16 |  | Prpoposed for shifting during 2019-24 to accommodate proposals as under
4 | Online DGA for Power Transformers | 3.5 |  |  | 3.5 |  | Prpoposed for shifting during 2019-24 to accommodate proposals as under
5 | Aerial Working Platform for Stage- 2 CW Motor ( Working Height >10 Mtr. ) | 0.2495 |  | 0.2495
6 | Ultrasound Based PD Detector for LT Switchgear | 0.16 |  | 0.16
7 | Portable Handheld Cable Fault Locator | 0.2 |  | 0.2
8 | Chain Pulley Blocks 15 Ton | 0.01 |  | 0.01 |  |  | Under award approval
9 | Chain Pulley Blocks 15 MT | 0.095 |  | 0.095 |  |  | Under award approval
10 | Battery Operated Trolley (10 MT) | 0.1 |  | 0.1
11 | DPRV- A of Seal Oil System | 0.5486 |  | 0.5486
12 | DPRV- B of Seal Oil System | 0.5486 |  | 0.5486
13 | Seal Oil Cooler Tube Nest of Seal Oil System | 0.4274 |  | 0.4274
14 | Self Cleaning Suction Strainer for ECW System | 0.652 |  | 0.652 |  |  | TS done; under QR evaluation
15 | MS Strainer for Stage-1 | 0.7847 |  | 0.7847 |  |  | Under award approval
16 | HRH Strainer for Stage-1 | 1.1523 |  | 1.1523 |  |  | Under award approval
17 | Air handling units (9 each) for Unit-1,3&4 | 1.48 |  | 1.48 |  |  | LOI Issued
18 | PLC upgradation in Ash mound area | 1.62 |  | 1.62 |  |  | Tech suitability done , Price Bid to be opened
19 | High lighting mast in Township | 0.46 |  | 0.46 |  |  | Under Tender Document preparation
20 | Supply and Installation of new In-Motion Weigh Bridge | 0.18 |  | 0.18 |  |  | Work in progress; cash flow to be done
21 | Procurement of flow meter | 0.88 |  | 0.88 |  |  | Price Bid opened
22 | Installation of variable frequency drive system for Vibro feeders in CHP Stg-1 | 0.18 |  | 0.18 |  |  | PO placed
23 | Installation of VFD with spacer coupling in both ID fans of Unit-2 | 2.83 |  | 2.84 |  |  | LOI Issued
| Total | 27.778 | 0 | 20.1484 | 7.63