## BTPS
Annexure-V (C)
Name of Generating Station : Badarpur Thermal Power Station
Stage:
COD of Units/Station
Details of expenditure incurred from Compensation Allowance and Special Allowance during Tariff Period 2009-14
FY Year | Add-cap allowed by the Commission under the provision of Regulation 9(2) |  | Compensatory allowance allowed by the Commission, if any | Special allowance allowed by the Commission, if any | Income tax rate | Effective Compensatory allowance available for Expenditure | Effective Special allowance available for Expenditure | Details of Asset/Work wise Capitalisation based on the Expenditure allowed by the Commission in the tariff period 2009-14 | [5 empty] | Total Capitalization under SA & CA | Capitalisation done which has not been claimed/ allowed in the tariff | Difference of Allowed vs Expenditure | Capital Spares | Total Addition during the year | Total Addition during the year as per duly audited Schedule of Fixed Asset | Variation if any to be reconciled /justified.
[8 empty] | Capitalisation out of add cap allowed under Regulation 9(2) |  | Capitalisation out of Compensation allowance in the stations wherever applicable |  | Capitalisation out of Special Allowance allowed in the stations where applicable
| Net Basis | Liability of col. (2) |  |  | (%) |  |  | Asset/work | Rs(Lakh) | Asset/work | Rs(Lakh)- Gross | Asset/work | (Rs. lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 = 4* 6 | 8 = 5 * 6 | 6 |  | 7 |  | 8 |  |  | 9 | 10=(2+3+4+5)-(6+7+8+9) | 11 | 12=6+7+8+9+11 | 13 | 14
2009-10 | 131.9 | 8.5813 | 0 | 0 |  |  |  | Replacement of existing Station Lighting Fixtures etc.* | 11.9789 | N/A | N/A | N/A | N/A | 0 | 2044.1587 | -2044.1629 | 1110.7951 | 3295.4392 | 2958.59 | Decap of MBOA: (-)6.53, Decap Spares: (-)325.72, Decap of Misc Assets: (-) 4.60
[8 empty] | Replacement of existing LT Power & Control cables.* | 1.38
[8 empty] | Replacement of online instrumentation in WTP* | 17.3252
[8 empty] | PLC based control system of OCHP* | 14.751
[8 empty] | Strengthening of chimneys* | 5.95
[8 empty] | UPS* | 43.6771
[8 empty] | Lab instruments* | 21.3865
[8 empty] | (Ash dyke) - construction of boundary wall for balance portion of ash dyke.* | 0.06447
[8 empty] | Ash Dyke - 1st raising of Ash Dyke Phase-V* | 4.3623
[8 empty] | 3rd Raising of Ash Dyke Phase-II* | 15.7
[8 empty] | ERP Implementation* | 3.91
[8 empty] | Total | 140.4855 | Total | 0 | Total | 0
2010-11 | 651.4793 | 27.3311 | 0 | 0 |  | 0 | 0 | Goods Lift No.2 & 3 (2 nos)* | 37.0366 | N/A | N/A | N/A | N/A | 0 | 145.4529 | -145.4518 | 1277.1921 | 2074.1243 | 1349.47 | Decap of MBOA: (-) 16.82, Decap Spares: (-)707.71
[8 empty] | Supply & Installation of ILMS & suspended magnets in CHP* | 61.0182
[8 empty] | Bridges over Gurgaon canal and Agra canal under deposit works by UPID & Haryana ID* | 449.619
[8 empty] | UPS* | 20.908
[8 empty] | Ash dyke 1st raising of Ash Dyke Phase-V.* | 12.7264
[8 empty] | Pay Loaders (2 Nos.)* | 51.7449
[8 empty] | Procurement of Portable Environment Monitoring Instruments* | 6.4872
[8 empty] | Instruments* | 10.8264
[8 empty] | Ambient Air Quality Monitoring System* | 1.1126
[8 empty] | Total | 678.8093 | Total | 0 | Total | 0
2011-12 | 2709.05 | 309.8754 | 0 | 0 |  | 0 | 0 | (Ash dyke) construction of boundary wall for balance portion of ash dyke.* | 89.5809 | N/A | N/A | N/A | N/A | 0 | 1154.6519 | -1154.6502 | 1908.8843 | 6082.7598 | 5226.78 | Decap Spares: (-) 855.91
[8 empty] | Shunting Loco WDS-6 (1No)* | 934.2303
[8 empty] | Inter connection to all under ground tanks for drinking water supply from Delhi Jal Board Mains.* | 18.5273
[8 empty] | DRY FLY ASH EXTRACTION SYSTEM* | 1826.2812
[8 empty] | New Coal Handling Plant * | 47.8204
[8 empty] | DIFFERNTIAL PRESSURE TRANSMITTER (Lab Instruments)* | 15.5139
[8 empty] | Laser Based Shaft alingnment Instrument (Lab Instruments)* | 3.2062
[8 empty] | L/A 198 KV SURGE COUNTER & CURRENT METER (Lab Instruments)* | 0.77504
[8 empty] | Dual Channel vibration analyzer cum data collector with software.* | 13.9679
[8 empty] | Approach road to Ash Silo Area | 3.5565
[8 empty] | Coal pick stone boundary wall for Ash Silo areas | 11.7087
[8 empty] | CISF Room in Ash Silo Area | 3.0436
[8 empty] | CCTV system - Des/Eng/Supply/Erec/Comm/Test | 50.7117
[8 empty] | Total | 3018.9236 | Total | 0 | Total | 0 | [7 empty] | #REF!
2012-13 | 934.26 | 20.2055 | 0 | 0 |  | 0 | 0 | Portable Effluent Analyser* | 9.792 | N/A | N/A | N/A | N/A | 0 | 2408.2234 | -2408.2245 | 1575.6836 | 4938.3736 | 4818.39 | Decap of MBOA: (-)1.22 , Decap Spares: (-) 118.06, IUT:3.02, ERV: (-), Assset Decap: (-) 3.72
[8 empty] | Dissolved Gas Analyser (TRANSFORMER OIL)* | 29.3394
[8 empty] | Design, supply, Installation, testing & Commisioning of Passenger Lift No. 2* | 32.2726
[8 empty] | Strengthening of Wagon Tippler -3 at BTPS* | 81.4211
[8 empty] | Plant Boundary wall* | 39.8421
[8 empty] | Laying of Water pipeline* | 11.5819
[8 empty] | 2nd Raising of Ash Dyke Phase - I* | 614.989
[8 empty] | Design , Erect &Comm of Ventilation system in CHP* | 12.793
[8 empty] | Dry Fly Ash Extraction System* | 121.4562
[8 empty] | Coal pick stone boundary wall for Balance portion of Ash dyke* | 0.010695
[8 empty] | Coal pick stone boundary wall for silo areas* | 0.96583
[8 empty] | Total | 954.4666 | Total | 0 | Total | 0
2013-14 | 527.26 | 6.8967 | 0 | 0 |  | 0 | 0 | Wheel loader as per specification (Pay Loaders.)* | 70.2986 | N/A | N/A | N/A | N/A | 0 | 1000.7401 | -1000.7433 | 1584.9368 | 3119.8368 | 2643.53 | Liablity Reversal: , Decap of MBOA: 54.97, Decap Spares: (-) 438.65, IUT: 17.31 , ERV: (-)
[8 empty] | BOUNDARY WALL:Boundary wall in Factory Plant* | 2.8057
[8 empty] | LABOUR REST ROOM (2*2 ROOMS)* | 51.2784
[8 empty] | Rain Water Harvesting System(Plant:Admin Building)* | 9.7089
[8 empty] | Renovation of quarters of T/s* | 114.2321
[8 empty] | OFF SITE BUILDING:RCC Tank* | 31.705
[8 empty] | BOUNDARY WALL:Boundary wall in Town ship* | 56.0914
[8 empty] | DRY ASH & FLY ASH EXTRACTION SYSTEM* | 2.4437
[8 empty] | OFF SITE BUILDING:Cooling Tower - III* | 91.7854
[8 empty] | OFF SITE BUILDING:Cooling Tower -IV* | 91.7854
[8 empty] | CCTV system - Des/Eng/Supply/Erec/Comm/Test* | 0.357
[8 empty] | Ozone Analyser* | 11.6684
[8 empty] | Total | 534.1599 | Total | 0 | Total | 0
Details of expenditure incurred from Compensation Allowance and Special Allowance during Tariff Period 2014-17
FY Year | Add-cap allowed by the Commission under the provision of Regulation 14(3) |  | Compensatory allowance allowed by the Commission, if any | Special allowance allowed by the Commission, if any | Income tax rate | Effective Compensatory allowance available for Expenditure | Effective Special allowance available for Expenditure | Details of Asset/Work wise Capitalisation based on the Expenditure allowed by the Commission in the tariff period 2009-14 | [5 empty] | Total Capitalization under SA & CA | Capitalisation done which has not been claimed/ allowed in the tariff | Difference of Allowed vs Expenditure | Capital Spares | Total Addition during the year | Total Addition during the year as per duly audited Schedule of Fixed Asset | Variation if any to be reconciled /justified.
[8 empty] | Capitalisation out of add cap allowed under Regulation 14(3) |  | Capitalisation out of Compensation allowance in the stations wherever applicable |  | Capitalisation out of Special Allowance allowed in the stations where applicable
| Net Basis | Liability of (2) |  |  | (%) |  |  | Asset/work | Rs(Lakh) | Asset/work | Rs(Lakh)- Gross | Asset/work | (Rs. lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 = 4* 6 | 8 = 5 * 6 | 6=1+2 |  | 7 |  | 8 |  |  | 9 | 10=(2+3+4+5)-(6+7+8+9) | 11 | 12=6+7+8+9+11 | 12 | 13
2014-15 | 6891.82 |  | 0 | 0 |  | 0 | 0 | Details as per Annexure-BTPS | 8178.6344 | N/A | N/A | N/A | N/A | 0 | 124.4914 | -1411.3058 | 2613.1525 | 10916.2782 | 9732.5636 | Decap of MBOA: (-) 60.80, Decap Spares: (-) 1116.56, IUT: (-)1.31 , Decap of ESP: (-) 5.04
2015-16 | 3512.14 |  | 0 | 0 |  | 0 | 0 | Details as per Annexure-BTPS | 7723.11 | N/A | N/A | N/A | N/A | 0 | 53.9988 | -4264.9688 | 3106.7664 | 10883.8752 | 9125.9509 | Asset Decap: (-)6.09, Decap of MBOA: (-)23.71, Decap Spares: (-) 1718.63, IUT: (-) 9.49
2016-17 | 481.32 |  | 0 | 0 |  | 0 | 0 | Details as per Annexure-BTPS | 1385.37 | N/A | N/A | N/A | N/A | 0 | 265.35 | -1169.4 | 809.67 | 2460.39 | 1964.28 | Deacp of Assets: (-)1.82, Decap of MBOA: (-)25.70, Decap of Spares: (-) 475.72, IUT: 7.13,

## Annexure
Annexure-BTPS
2014-15
Annexure
Sl. No. | Description | Allowed by CERC | Actual Capitalization | Justification/ Reason
1 | Augmentation of ESP | 3615 | 3614.5436
2 | Strenthening of Conveyor Structure in CHP Area. | 547.28 | 525.6235
3 | Closed Cycle Cooling Water System | 413.55 | 299.1546
4 | Procurement of Fire Tender (2 No.) | 73.62 | 78.0494
5 | 2nd raising of Ash Dyke Phase V alongwith with associated pipes and pump | 1322.93 | 1352.093
6 | Renovation of quarters of BTPS T/ship | 742.54 | 750.8041
7 | Renovation & Extension of BTPS Dispensary. | 123.21 | 136.3411
8 | Renovation of services Complex housing Bank, Post office etc. | 53.69 | 62.8249
9 | Modification in HPH & LPH Drip System in Unit IV & V( 2x210 MW) | 0 | 56.5584 | New Scheme
10 | R&M of 220 KV Switchyard | 0 | 32.1253 | New Scheme
11 | Renovation of lighting system | 0 | 25.336 | New Scheme
12 | Rain water harvesting | 0 | 4.7048 | New Scheme
13 | Labour rest rooms | 0 | 7.7535 | New Scheme
14 | Boundary wall in Township | 0 | 1.1606 | New Scheme
15 | Installation of Flow Measuring Device (Water Meter) | 0 | 4.2398 | New Scheme
16 | Procurement of dozer (5 No) | 0 | 895.464 | New Scheme
17 | SODIUM ANALYSER 0 - 10000 PPB | 0 | 22.0474 | New Scheme
18 | TURBIDITY SENSOR & TXR & IND | 0 | 23.6963 | New Scheme
19 | MBOA | 0 | 286.1141 | New Scheme
| Total | 6891.82 | 8178.6344
2015-16
Sl. No. | Description | Allowed by CERC | Actual Capitalization | Justification/ Reason
1 | Augmentation of ESP | 208 | 3917.8409
2 | Closed Cycle Cooling Water System | 1361 | 86.2159
3 | Renovation of quarters of BTPS T/ship | 6 | 6.2958
4 | Renovation of services Complex housing Bank, Post office etc. | 3 | 2.2906
5 | Continuous Emmission Monitoring System | 85.99 | 96.3453
6 | Procurement of one (01) No. Locomotive 1350 HP | 948 | 947.4959
7 | Procurement of five (05) Nos. of BEML BD -1 Dozers | 896 | 0 | Capitalized in 2014-15
8 | Installation of CCTV System (12 nos) | 4.15 | 5.3665
11 | IInd raising of Ash Dyke Phase V | 0 | 112.4652 | Balance work of scheme capitalized in 2014-15
9 | Renovation of lighting system | 0 | 39.3287 | New Scheme
10 | Reverse Osmosis and Sewage Treatment Plant | 0 | 1479.5253 | New Scheme
12 | Modification in HPH & LPH Drip System in Unit IV & V | 0 | 36.247 | New Scheme
13 | Energy Efficient Cartridge of BFP | 0 | 661.4419 | New Scheme
14 | Effluent Quality Management System | 0 | 34.6133 | New Scheme
15 | Excavator- 20 Ton Class | 0 | 78.6493 | New Scheme
16 | ABT Energy Metering System with Software | 0 | 49.2278 | New Scheme
17 | MBOA | 0 | 150.8767 | New Scheme
18 | Portable Alloy Analyzer | 0 | 17.7378 | New Scheme
19 | Conductivity Analyzer | 0 | 1.1433 | New Scheme
| Total | 3512.14 | 7723.1072
2016-17
Sl. No. | Description | Allowed by CERC | Actual Capitalization | Actual Capitalization
1 | Closed cycle cooling water system including RO/ STP, hot water duct & CT cell refurbishment | 125 | 181.3676
2 | Workshop Building | 49.79 | 54.779
3 | Renovation of stores: construction of additional store building | 148.5 | 258.736
4 | Drainage and sewage system upgradation of township of BTPS including rain water harvesting | 45 | 27.4736
5 | Continious Emission Monitoring System (Online monitoring instruments in chimney) | 8 | 6.102
6 | Renovation of service complex housing, bank, post office etc. | 0 | 2.6607 | Allowed in 2014-15 & 2015-16 | Allowed in 2014-15 & 2015-16
7 | Hydraulic operated arial tower wagon platform | 18 | 26.5681
8 | Passenger lift in TG Hall | 0 | 26.6119 | Allowed 28.80 Lakhs in 2017-18 & 2018-19 | Allowed 28.80 Lakhs in 2017-18 & 2018-19
9 | Strengthening of various structures in turbine & boiler Area | 0 | 77.3331 | Allowed 80 Lakhs in 18-19 | Allowed 80 Lakhs in 18-19
10 | Air conditioning system based on screw chiller | 0 | 133.0825 | Allowed 171.90 Lakhs in 2017-18 & 18-19 | Allowed 171.90 Lakhs in 2017-18 & 18-19
11 |  |  | 794.7145
12 | Energy Efficient Cartridge of BFP | 0 | 225.4007 | New Scheme | New Scheme
13 | Inflatable Jack 40T to 50 T | 0 | 3.4249 | New Scheme | New Scheme
14 | Battery operated Truck | 0 | 4.0507 | New Scheme | New Scheme
15 | Neutral Grounding Transformers St-II | 0 | 92.6248 | New Scheme | New Scheme
16 | Procurement of UAT | 0 | 265.1581 | New Scheme | New Scheme
17 |  | 87.03
| Total | 481.32 | 2180.0881

## XVI A_VSTPS_V (hidden)
Annexure XVI A
Details of Incidental Expenses during Construction (IDEC) with break-up for the Generating stations for which COD is declared after 1.4.2014
Name of Generating Station : Vindhyachal STP Stage- V
Stage : Stage - V
COD of Units/Station : 30.10.2015
Rs-Lac
S. No. | Item-wise details of expenditure with break-up | Expenditure as on SCOD | Expenditure as on actual COD of unit/ station | Time Overrun
A | Head of Expenses: |  |  | No
1 | Const Power Chrgs | 5275.9295 | 5275.9295
2 | IEDC Allocated by CC (Capital) | 2913.1078 | 2913.1078
3 | Salaries | 2595.5164 | 2595.5164
4 | Contribution to PF | 379.653 | 379.653
5 | Employee Welfare Exp. | 112.2326 | 112.2326
6 | R&M - Bldg | 35.7926 | 35.7926
7 | R&M - Others | 163.4667 | 163.4667
8 | Rates & Taxes | 6.0843 | 6.0843
9 | Communication Exp | 14.1198 | 14.1198
10 | Bank Charges | 1.8814 | 1.8814
11 | Travel Expenses | 164.4169 | 164.4169
12 | Tender Expenses | 71.3213 | 71.3213
13 | Advertisement & Publicity | 2.0828 | 2.0828
14 | Security Exp | 72.2292 | 72.2292
15 | Entertainment Exp | 10.6657 | 10.6657
16 | Professional Charges | 4.7648 | 4.7648
17 | Legal Exp | 9.197 | 9.197
18 | Printing exp | 0.06006 | 0.06006
19 | Transport vehicle Running Exp | -3.5693 | -3.5693
20 | Misc Exp | 1836.7101 | 1836.7101
21 | Depreciation (Tangible Assets) | 264.7635 | 264.7635
22 | Depreciation (Intangible Assets) | 0 | 0
A | Total Expenses | 13930.4262 | 13930.4262
B | Head of Income | 0 | 0
1 | Misc Income | 28.2195 | 28.2195
2 | Power Charges Recovery | 40.2799 | 40.2799
3 | Interest from Contractors | 117.5189 | 117.5189
4 | Water Charges Recovery | 0.00327 | 0.00327
5 | Hire Charges Recovery | 0.47368 | 0.47368
B | TOTAL INCOME | 186.4953 | 186.4953
|  | 0 | 0
A-B | NET TOTAL | 13743.9309 | 13743.9309
| Capitalised on COD | 12492.96 | 12492.96
| Balance in CWIP on COD | 1250.9709 | 1250.9709